## ProductBacklog
Java Stream Case Study - FSE Program
Project Scope: Inventory Management System (IMS) should be able to fetch all the essential details by hitting vendor and material services and hold functionalities to help insert purchase details
No | Product Backlog Items
1 | Invoking Vendor Micro Service for fetching Vendor Information
2 | Invoking Material Micro Service for fetching details of Materials available.
3 | Registering the purchases made with different Vendors and Retrieving the details of materials purchased from a selected vendor between specified dates.
Product Backlog Items and Requirement Description
No | Product Backlog Items | User Story Title | Requirement Description
1 | Invoking Vendor Micro Service for fetching Vendor Information | Vendor Microservice | This requirement focuses on building and deploying vendor micro service application So that all the vendor details can be fetched from the service which helps to generate a Purchase Entry in our application.
2 | Invoking Material Micro Service for fetching details of Materials available | Material Microservice | This requirement focuses on building and deploying material micro service application So that all the material details can be fetched from the service which helps to generate a Purchase Entry in our application.
3 | Registering the purchases made with different Vendors and Retrieving the details of materials purchased from a selected vendor between specified dates | Material Purchase Entry | This requirement focuses on saving the materials purchased from different vendors in IMS database, So that the purchase details are maintained internally which helps retrieving materials purchased from a selected vendor between specified dates.

## UserStories
Java Stream Case Study - FSE Program
Project Scope: Inventory Management System (IMS) should be able to fetch all the essential details by hitting vendor and material services and hold functionalities to help insert purchase details
Functionality: This user story focuses on building and deploying vendor micro service application. So that all the vendor details can be fetched from the service which helps to generate a Purchase Entry in our application.
Id: UserStory-01 User Story Title: Vendor Microservice
Narrative: As a developer, I want to build and deploy vendor service application So that all the vendor details are provided as a service
Acceptance Criteria:
1. Import the vendor service project structure provided
2. Create a REST service to fetch list of vendors from DB
3. Create JUnit test classes for vendor controller, service and DAO classes
4. Run and test vendor application
Functionality: This user story focuses on building and deploying material micro service application. So that all the material details can be fetched from the service which helps to generate a Purchase Entry in our application.
Id: UserStory-02 User Story Title: Material Microservice
Narrative: As a developer, I want to build and deploy material service application So that all the material details are provided as a service
Acceptance Criteria:
1. Import the material service project structure provided
2. Create a REST service that fetches material category list from DB
3. Create a REST service that fetches material type list for the chosen category from DB
4. Create a REST service that fetches unit list for the chosen category from DB
5. Create JUnit test classes for all material controllers, services and DAO classes
6. Run and test material application.
Functionality: This user story focuses on saving the materials purchased from different vendors in IMS database, So that the purchase details are maintained internally which helps retrieving materials purchased from a selected vendor between specified dates.
Id: UserStory-03 User Story Title: Material Purchase Entry
Narrative: As an IMS user, I want to save the material purchase details from vendors in IMS purchase database So that the purchase details are maintained which helps retrieving materials purchased from a selected vendor between specified dates
Acceptance Criteria:
1. Create purchase bean, vendorwise purchase report bean and purchase entity classes
2. Create a REST client to retrieve vendor list using vendor microservice
3. Create a REST client to retrieve material category list using material microservice
4. Create a REST client to retrieve material type list specific to a material category using material microservice
5. Create a REST client to retrieve unit list specific to a material category using material microservice
6. Create a React application that allows users to:View the Home Page. Enter a Purchase Order. View Purchase Order Success Confirmation.Generate and display purchase reports for a selected vendor within a specified date range.Use modern React practices, HTML5, and CSS3 for UI design.
7. Add spring form validations to PurchaseEntry page
8. Add PurchaseEntryController, ReportsController, Service and DAO classes
9. Create JUnit test classes for all IMS controllers, services and DAO classes
10. Run and test IMS application

## StoryPoints&SprintPlan
Java Stream Case Study - FSE Program
Project Scope: Inventory Management System (IMS) should be able to fetch all the essential details by hitting vendor and material services and hold functionalities to help insert purchase details
User Story | User Story Title | Priority | Story Points | Note: 1. Enter the story points identified against each story, so that total story points will be calculated automatically. 2. Update the team size value, if it is different. So that the initial Team Velocity will be calculated automatically. 3. Based on the total Story Points and Team's Veocity, number of Sprint will be calculated automatically 4. Capture the user stories to be completed on each Sprint
UserStory-01 | Vendor Microservice | Must Have | 0
UserStory-02 | Material Microservice | Must Have | 0
UserStory-03 | Purchase Entry | Must Have | 0
Total |  |  | 0
Inventory Management System - Sprint Release Plan
Enter Team Size | 5 | Team velocity = Total Days of App Development * Team Size * 0.6 (approximate productive time in hours) |  |  | 15
Number of Sprints = Total Story points / Velocity |  |  | 0
Sprint 1 | Story Points | Sprint 2 | Story Points | Sprint 3 (If required) | Story Points
| 0 |  | 0 |  | 0
| 0 |  | 0 |  | 0
Total | 0 | Total | 0 | Total | 0

## ActivityEffortEstimation
Java Stream Case Study - FSE Program
Project Scope: Inventory Management System (IMS) should be able to fetch all the essential details by hitting vendor and material services and hold functionalities to help insert purchase details
User Story Id | User Story Title | Identified Tasks | Task Id | Owner | Estimation - Effort and Task Completion Status |  | High Level View - Task Completion Status
[5 empty] | Effort in hours | To be Completed on | Day | No. of Tasks to be Completed
UserStory-01 | Vendor Microservice | Import the vendor service project structure provided | Task-01 |  |  |  | Day 1 | 0
|  | Create a REST service to fetch list of vendors from DB | Task-02 |  |  |  | Day 2 | 0
|  | Create JUnit test classes for vendor controller, service and DAO classes | Task-03 |  |  |  | Day 3 | 0
|  | Run and test vendor application | Task-04 |  |  |  | Day 4 | 0
UserStory-02 | Material Microservice | Import the material service project structure provided | Task-05 |  |  |  | Day 5 | 0
|  | Create a REST service that fetches material category list from DB | Task-06
|  | Create a REST service that fetches material type list for the chosen category from DB | Task-07
|  | Create a REST service that fetches unit list for the chosen category from DB | Task-08
|  | Create JUnit test classes for all material controllers, services and DAO classes | Task-09 | [5 empty] | Day 1
|  | Run and test material application | Task-10 | [5 empty] | Day 2
UserStory-03 | Purchase Entry | Create purchase bean, vendorwise purchase report bean and purchase entity classes | Task-11 | [5 empty] | Day 3
|  | Create a REST client to retrieve vendor list using vendor microservice | Task-12 | [5 empty] | Day 4
|  | Create a REST client to retrieve material category list using material microservice | Task-13 | [5 empty] | Day 5
|  | Create a REST client to retrieve material type list specific to a material category using material service | Task-14
|  | Create a REST client to retrieve unit list specific to a material category using material microservice | Task-15
|  | Create a React application that allows users to: View the Home Page. Enter a Purchase Order. View Purchase Order Success Confirmation. Generate and display purchase reports for a selected vendor within a specified date range. Use modern React practices, HTML5, and CSS3 for UI design.` | Task-16
|  | Implement validation in React components by validating mandatory fields, numeric inputs, date ranges, input formats, displaying appropriate error messages below fields, preventing form submission on validation failures, and providing visual feedback for valid/invalid inputs. | Task-17
|  | Add PurchaseEntryController, ReportsController, Service and DAO classes | Task-18
|  | Create JUnit test classes for all IMS controllers, services and DAO classes | Task-19
|  | Run and test IMS application | Task-20
Total Number of Tasks |  |  | 20 | Total Hours | 0

## ActivityTracker
Java Stream Case Study - FSE Program
Project Scope: Inventory Management System (IMS) should be able to fetch all the essential details by hitting vendor and material services and hold functionalities to help insert purchase details
| Activity Details & Effort Estimation |  |  |  | Day of Sprint, Actual Effort & Status of Activity
Backlog Item | UserStory Id | Task | Owner | Estimated Effort | Day 1 | Status | Day 2 | Status | Day 3 | Status | Day 4 | Status | Day 5 | Status
User Story 1 - build and deploy vendor application. So that all the vendor details are provided as a service | UserStory-01 | Task-01 | 0 | 0
|  | Task-02 | 0 | 0
|  | Task-03 | 0 | 0
|  | Task-04 | 0 | 0
User Story 2 - build and deploy material application. So that all the material details are provided as a service | UserStory-02 | Task-05 | 0 | 0
|  | Task-06 | 0 | 0
|  | Task-07 | 0 | 0
|  | Task-08 | 0 | 0
|  | Task-09 | 0 | 0
|  | Task-10 | 0 | 0
User Story 3 | UserStory-03 | Task-11 | 0 | 0
|  | Task-12 | 0 | 0
|  | Task-13 | 0 | 0
|  | Task-14 | 0 | 0 | [10 empty] | Tasks Completed on a day | Completed
|  | Task-15 | 0 | 0 | [10 empty] | Hours spent on a day | Pending
|  | Task-16 | 0 | 0
|  | Task-17 | 0 | 0
|  | Task-18 | 0 | 0
|  | Task-19 | 0 | 0
|  | Task-20 | 0 | 0
| Total |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## BurnDownChart
Java Stream Case Study - FSE Program
Project Scope: Inventory Management System (IMS) should be able to fetch all the essential details by hitting vendor and material services and hold functionalities to help insert purchase details
Burn Down Chart - Inventory Management System
Total Number of Tasks - 20
No | Days | Estimated Tasks remaining | Actual Tasks Remaining
1 | Day 0 | 20 | 20
2 | Day 1 | 20 | 20
3 | Day 2 | 20 | 20
4 | Day 3 | 20 | 20
5 | Day 4 | 20 | 20
6 | Day 5 | 20 | 20
No | Day | Tasks to be completed | Actual Tasks Completed
1 | Day 1 | 0 | 0
2 | Day 2 | 0 | 0
3 | Day 3 | 0 | 0
4 | Day 4 | 0 | 0
5 | Day 5 | 0 | 0
Total |  | 0 | 0